## Checklist
CheckList
| Description | Yes | No
1 | Material Delivery
Is the thickness of HDPE membrane 1.2 mm?
Material test certificate received?
2 | Installation
Is the surface clean and free from any loose material?
Is the surface free from protrusions and smooth to receive membrane?
Is there any standing water over substrate?
Is the membrane laid with non-adhesive side towards PCC?
Is there overlap of 70-80 mm between two sheets of HDPE membrane?
Are the overlaps proper without any adhesion issues?
Are the ends properly bonded with double side adhesive tapes?
Is HDPE membrane applied at least 500mm away from reinforcement?
Is HDPE membrane laid on the shuttering side of vertical face?
3 | Post Membrane Installation (Pre-Concreting)
Is there any puncture to the HDPE membrane?
Is there any damage at the joining of the two adjacent membrane?
Was there any repair of membrane done by the waterproofing contractor?
If yes has the damage been completely repaired?
Have the repair patches been plotted on as built drawing, for future reference?
Has the waterproofing contractor inspected the membrane and approved concrete pour?
4 | Post Concreting
Is there any upliftment of concrete on edges?
Any visible defects in concrete?